## Sheet1
Time from show date | Are we attending? | Actions Sales Admin need to take
8-12 months from show date | Not decided yet | Determine from Sales team if this is a show we want to invest in. It's important to do this early, some of the larger shows we attend have early applications and deadlines to select booths months in advanced of the show. This is when booth size isually determined. (Example: the PSP21 Expo- We were informed in Feb that booth selection was March 1st for a show in November)
| No | Let the Sales Admin Lead know so they can update the Tradeshow calendar
| Yes | If we have attended in the year prior, fill out the last show work sheet. This will help remember key details on last year's event found here: | S:\Sales & Marketing\Advantus 2.0 Project\Wiki 2.0 Documentation
|  | Begin to fill out the current year's worksheet here: If details are not available yet, please contact the show and ask when they will be. Set a calendar reminder to check back around that time. IF possible, ask for the Exhibitor Manual. | Editable_Tradeshow Worksheet.pdf
Let the Sales Admin Lead know so they can update the Tradeshow calendar
If registration is open, book the show
Review hotel booking details, large show require you to book hotels in blocks. Booking may open 6-8 months before the show.
5-6 months from the show date |  | If registration was not open prior, go ahead a book show
Determine a shipdate. This is the date your supplies will ship. Anything shipping will need to be packed and ready before this date.
Create Binder (you can print information as you go) with the following tabs: Exhibitor Contract Travel details Show info Shipping information Badges
Review show rules, regulations and policies. They often affect setup of the booth, signs, and other items. If this is your first time coordinating this show, make sure to share these with the Marketing Manager and the Sales Admin lead to review as well.
Before the kick off meeting with Sales staff, have them fill out the Tradeshow Planning survey: I will add link.
Mark up catalogs and sell sheets to remove obsolete items- Do this prior to your meeting with sales so you go into the meeting knowledgable about the product and what needs to be updated.
Set up a time to meet with Sales to determine their goals for the show- is it write orders? Is it just to get exposure to a new audience? Other topics to discuss: Who is attending? Who will be responsible for setting up? Do we need electric or other show services? Which samples will we be bringing to the show? If they do not have list prepared, make a plan for sales to provide this by a certain date. Should we have a show special? Do we need a closeout list? How do we want to display samples? Signage Will we need props or bag stuffing? Do we want to hold a giveaway to attract people to the booth? Do we want to use a lead retrevial system? If not, how are we going to collect information from potential customers? Do we need nametags or shirts? Do we have preferences on who books travel? Do they have a preference on hotel? Do they need to rent a car? Do they have reward or membership numbers that you should use when booking? What literature do we want to bring? How many catalogs? If we need sell sheets, what products need them? Do we need order forms? If so, are these for internal use or for writing show orders?
Go to the warehouse and review the crates. If needed, ask the warehouse staff to make repairs or build new crates as needed
Register for Badges
Buy any booth items needed (display units, slatwall, props, make and take supplies, giveaways etc.)
Request booth signage, updated catalog proof, Digital booth mock from graphics
2-3 months from the show date |  | Review and summarize the marketing opportunities available at the show. Submit to Marketing Manager who can discuss with VP of Marketing.
Book or ship flooring for booth space, if it is not included in the price of booth space.
Book or ship furniture, merchandising units and accessories for booth space (ex: chair, showcase, table, shelving, display accessories, peg hooks, etc.).
Request booth signage from graphics.
Book Services including: Labor Carpet Electrical supply
Book a lead retrieval scanner if applicable
|  | Book Internet and telecommunications services | Do we ever do this?
Set up a time with the Sales Admin lead to go to the warehouse and set up the booth prior to packing and shipping.
Submit graphics request. All signage, graphics materials should be done 3-4 weeks prior to pack and ship date to ensure that graphics has enough time to design and obtain everythign they need to purchase
Book hotels and flights (should be done a minimum of 21 days in advanced for best rates)
Put together a closeout list
Order marketing samples (should be done about 1 week prior to when you want to pack and ship OR 1 week prior to when you need to go to the warehouse to set up the booth prior to shipping).
1-2 months prior to the show |  | Arrange for miscellaneous booth items (ex: extension cords, surge protector, garbage bags, thin wire to fix or hang items, Scotch tape, packing tape, scissors, Velcro strips or tabs, pens, pencils, paper, stapler, staples).
Pack and ship show. Make sure to ship everything needed included: Flooring Displays/Merchandizing units Furniture Lighting Existing and new Merchandize in booth.
Request insurance information from compliance, if necessary
Prepare to ship tradeshow return paperwork (ex: choose a carrier, prepare necessary shipping paperwork such as waybills and shipping labels that include your return address)
3-4 weeks prior to show |  | Arrange booth attire- shirts, nametags, etc.
Submit per diems for all attendees if applicable.
If we need to utilize computers while there, finalize these plans with IT
Pack several box cutters in your checked suitcase to easily retrieval upon your arrival.
Ship any last minute sample arrivals directly to the show venue.
Carry an adequate supply of business cards.
Carry a lead card, a notebook or both
Arrange for a container to use in collecting business cards
Pack miscellaneous items like hand sanitizer, throat lozenges, bottled water and small food snacks.
Ship necessary items to your hotel (call hotel to confirm S&H fee) or directly to the trade show venue.
At the show |  | Once booth is set up, take lots of pictures. Remember to get to focus on the details.

## C&H Specific tasks
Craft & Hobby
September | Ask Creative Directors for each brand for any changes to the booth layout/structure/displays/signage, don’t forget Tracia
Register for Crafters Home presentations/workshops if desired by each brand
Contact Tracia for the new Sulyn items to include
Begin figuring out giveaways for each brand as decided on by Director or Marketing and Product Development
Discuss make and take projects for each brand
Upload new item pricing for Tim Holtz
October | Send off any art that will be printed off-site
Ask Erica and Rana what the order minimum will be for the show special
Contact Tracia to figure out which products she specifically wants displayed in the booth, we usually do not have enough room for all Sulyn items
Track all new release samples that arrive in. Make sure new items are being photographed by Graphics.
Have Graphics create a pre-show and during the show e-blast
Plan group dinner
Go through all crates and make sure all product is packed and in good condition, we should have 2 of each item. At least 3 of each new release. Place a sample order for any product needed Buy any materials needed, pallet wrap, tape, etc.
Create/edit order forms for all brands. Save on the S drive by brand/type.
Finalize all Shipping Information using the CHA Freight Checklist
Submit products for Hot Product Showcase
November | Book flights for all attendees not booking their own
Book rental car if needed- make sure company and pick-up/drop-off site is on location at airport
Upload new item pricing for Cosmo Cricket, Storage, Sulyn and McGill
Register for electrical, rigging, carpet and labor services
Submit booth layout drawing to show and Labor Supervisor
Complete new item set up forms for distributors and mail samples. Bring any remaining samples to the show to give. Send Confidentiality Agreement.
December | Submit per diem requests to Accounting
Pack any signage printed in-house (in-booth signage, display posters, etc.)
Make final crate list
Pack 2 rolls of bubble wrap, roll of labels (to label bins/boxes), large sharpies and empty flat boxes with booth
Schedule e-blasts and provide links to Web Specialist
Print shipping labels to and from the show (75 return labels)
Ship crates to Advance Warehouse designated by the show and get Bill of Lading from Shipping
Set aside one sample of each new product for the Product Development New Item meeting
Bring back one carton of catalogs to corporate and distribute to Marketing, Product Development, Customer Service and Purchasing
Contact Nancy McNally at Scrapbookupdate.com and Scrapbook.com for Tim Holtz blog shares of new releases